## Cover
Work Breakdown Structure (WBS)
TAT: Resource Management — Excavation and Lining Operations
Project context
Sub-project of the Trans-under-Atlantic Tunnel programme. Covers planning, excavation, lining and sealing, quality assurance, and maintenance handover for one delivery iteration.
Workbook contents
Cover | Project context and workbook guide
WBS | Full hierarchical breakdown — 5 phases, 69 activities
Phase Summary | Activity counts and notes by phase

## WBS
Work Breakdown Structure
5 phases · 69 activities
WBS ID | Level | Phase / Activity | Notes
1.0 | Phase | Design & Planning | 15 activities
1.1 | Activity | Conduct site survey and environmental assessment
1.2 | Activity | Define required skill sets for each role
1.3 | Activity | Post job openings and recruit personnel
1.4 | Activity | Screen applicants for qualifications
1.5 | Activity | Schedule interviews with shortlisted candidates
1.6 | Activity | Develop safety protocols and initial risk assessment
1.7 | Activity | Identify and evaluate potential suppliers for materials
1.8 | Activity | Negotiate and finalise contracts with suppliers
1.9 | Activity | Plan facility layout for optimal resource flow
1.10 | Activity | Define equipment specifications and requirements
1.11 | Activity | Assign project team roles and responsibilities
1.12 | Activity | Conduct project kickoff meeting
1.13 | Activity | Develop communication plan for project updates
1.14 | Activity | Schedule initial maintenance setup for key equipment
1.15 | Activity | Document all planning procedures and decisions
2.0 | Phase | Excavation | 15 activities
2.1 | Activity | Set up and test the Tunnel Boring Machine (TBM)
2.2 | Activity | Begin primary excavation work
2.3 | Activity | Implement safety protocols for excavation
2.4 | Activity | Assign labourers and establish excavation schedules
2.5 | Activity | Arrange for material deliveries and debris removal logistics
2.6 | Activity | Perform daily safety briefings for excavation team
2.7 | Activity | Monitor material usage and reorder levels for excavation
2.8 | Activity | Establish communication channels for excavation progress
2.9 | Activity | Coordinate waste removal and recycling during excavation
2.10 | Activity | Conduct quality checks on TBM performance
2.11 | Activity | Perform weekly equipment maintenance and repairs
2.12 | Activity | Document excavation progress and update project timeline
2.13 | Activity | Coordinate transportation for debris disposal
2.14 | Activity | Train workers on emergency evacuation procedures
2.15 | Activity | Adjust excavation plan based on ground conditions
3.0 | Phase | Lining & Sealing | 15 activities
3.1 | Activity | Begin concrete mixing and tunnel lining installation
3.2 | Activity | Monitor inventory levels of concrete and sealing materials
3.3 | Activity | Assign equipment operators for lining and sealing machinery
3.4 | Activity | Establish waterproofing procedures and apply sealants
3.5 | Activity | Schedule ventilation and drainage installation activities
3.6 | Activity | Conduct safety checks for lining and sealing operations
3.7 | Activity | Monitor temperature and humidity during concrete setting
3.8 | Activity | Perform bi-weekly maintenance on lining equipment
3.9 | Activity | Document material usage and monitor stock levels
3.10 | Activity | Review and inspect installed lining for quality control
3.11 | Activity | Coordinate logistics for sealant material deliveries
3.12 | Activity | Update project timeline based on sealing phase progress
3.13 | Activity | Inspect and adjust ventilation equipment installation
3.14 | Activity | Establish fire safety protocols for sealing materials
3.15 | Activity | Conduct training for workers on sealant application
4.0 | Phase | Quality Assurance | 8 activities
4.1 | Activity | Conduct structural and safety inspections for completed sections
4.2 | Activity | Review quality of materials used in each phase
4.3 | Activity | Conduct system testing for tunnel safety
4.4 | Activity | Perform final adjustments as needed based on inspection results
4.5 | Activity | Document results of quality inspections and system tests
4.6 | Activity | Perform a comprehensive maintenance inspection of all equipment
4.7 | Activity | Schedule additional repairs or adjustments as needed
4.8 | Activity | Finalise safety protocols for completed tunnel sections
5.0 | Phase | Maintenance & Control | 16 activities
5.1 | Activity | Update equipment records and document condition for handover
5.2 | Activity | Develop a punch list of items needing adjustment
5.3 | Activity | Conduct follow-up inspections to ensure all adjustments are complete
5.4 | Activity | Coordinate final approval from safety inspectors
5.5 | Activity | Perform mock drills for emergency preparedness
5.6 | Activity | Organise a project review meeting for quality assessment
5.7 | Activity | Finalise and distribute quality inspection reports
5.8 | Activity | Develop a preventive maintenance schedule for equipment
5.9 | Activity | Assign maintenance personnel for routine tasks
5.10 | Activity | Perform monthly preventive maintenance checks
5.11 | Activity | Conduct quarterly inspections of heavy machinery
5.12 | Activity | Review and update equipment maintenance logs
5.13 | Activity | Establish spare parts inventory and reorder levels
5.14 | Activity | Train maintenance staff on critical equipment handling
5.15 | Activity | Conduct final equipment inspections before handover
5.16 | Activity | Archive all maintenance and project documentation

## WBS Hierarchy
WBS — Indented Hierarchy
TAT: Resource Management — 5 phases · 69 activities
0.0 | TAT: Resource Management
1.0 | Design & Planning
1.1 | Conduct site survey and environmental assessment
1.2 | Define required skill sets for each role
1.3 | Post job openings and recruit personnel
1.4 | Screen applicants for qualifications
1.5 | Schedule interviews with shortlisted candidates
1.6 | Develop safety protocols and initial risk assessment
1.7 | Identify and evaluate potential suppliers for materials
1.8 | Negotiate and finalise contracts with suppliers
1.9 | Plan facility layout for optimal resource flow
1.10 | Define equipment specifications and requirements
1.11 | Assign project team roles and responsibilities
1.12 | Conduct project kickoff meeting
1.13 | Develop communication plan for project updates
1.14 | Schedule initial maintenance setup for key equipment
1.15 | Document all planning procedures and decisions
2.0 | Excavation
2.1 | Set up and test the Tunnel Boring Machine (TBM)
2.2 | Begin primary excavation work
2.3 | Implement safety protocols for excavation
2.4 | Assign labourers and establish excavation schedules
2.5 | Arrange for material deliveries and debris removal logistics
2.6 | Perform daily safety briefings for excavation team
2.7 | Monitor material usage and reorder levels for excavation
2.8 | Establish communication channels for excavation progress
2.9 | Coordinate waste removal and recycling during excavation
2.10 | Conduct quality checks on TBM performance
2.11 | Perform weekly equipment maintenance and repairs
2.12 | Document excavation progress and update project timeline
2.13 | Coordinate transportation for debris disposal
2.14 | Train workers on emergency evacuation procedures
2.15 | Adjust excavation plan based on ground conditions
3.0 | Lining & Sealing
3.1 | Begin concrete mixing and tunnel lining installation
3.2 | Monitor inventory levels of concrete and sealing materials
3.3 | Assign equipment operators for lining and sealing machinery
3.4 | Establish waterproofing procedures and apply sealants
3.5 | Schedule ventilation and drainage installation activities
3.6 | Conduct safety checks for lining and sealing operations
3.7 | Monitor temperature and humidity during concrete setting
3.8 | Perform bi-weekly maintenance on lining equipment
3.9 | Document material usage and monitor stock levels
3.10 | Review and inspect installed lining for quality control
3.11 | Coordinate logistics for sealant material deliveries
3.12 | Update project timeline based on sealing phase progress
3.13 | Inspect and adjust ventilation equipment installation
3.14 | Establish fire safety protocols for sealing materials
3.15 | Conduct training for workers on sealant application
4.0 | Quality Assurance
4.1 | Conduct structural and safety inspections for completed sections
4.2 | Review quality of materials used in each phase
4.3 | Conduct system testing for tunnel safety
4.4 | Perform final adjustments as needed based on inspection results
4.5 | Document results of quality inspections and system tests
4.6 | Perform a comprehensive maintenance inspection of all equipment
4.7 | Schedule additional repairs or adjustments as needed
4.8 | Finalise safety protocols for completed tunnel sections
5.0 | Maintenance & Control
5.1 | Update equipment records and document condition for handover
5.2 | Develop a punch list of items needing adjustment
5.3 | Conduct follow-up inspections to ensure all adjustments are complete
5.4 | Coordinate final approval from safety inspectors
5.5 | Perform mock drills for emergency preparedness
5.6 | Organise a project review meeting for quality assessment
5.7 | Finalise and distribute quality inspection reports
5.8 | Develop a preventive maintenance schedule for equipment
5.9 | Assign maintenance personnel for routine tasks
5.10 | Perform monthly preventive maintenance checks
5.11 | Conduct quarterly inspections of heavy machinery
5.12 | Review and update equipment maintenance logs
5.13 | Establish spare parts inventory and reorder levels
5.14 | Train maintenance staff on critical equipment handling
5.15 | Conduct final equipment inspections before handover
5.16 | Archive all maintenance and project documentation
Legend
Project root
Phase 1 — Design & Planning
Phase 2 — Excavation
Phase 3 — Lining & Sealing
Phase 4 — Quality Assurance
Phase 5 — Maintenance & Control

## WBS Tree
WBS Tree — SmartArt View
TAT: Resource Management — 5 phases · 69 activities
Overview — Project to Phases
TAT: Resource Management
1.0 Design & Planning |  | 2.0 Excavation |  | 3.0 Lining & Sealing |  | 4.0 Quality Assurance |  | 5.0 Maintenance & Control
Phase Detail — Activities by Phase
1.0 Design & Planning (15 activities)
1.1 Conduct site survey and environmental assessment | 1.2 Define required skill sets for each role |  | 1.3 Post job openings and recruit personnel | 1.4 Screen applicants for qualifications | 1.5 Schedule interviews with shortlisted candidates |  | 1.6 Develop safety protocols and initial risk assessment | 1.7 Identify and evaluate potential suppliers for materials | 1.8 Negotiate and finalise contracts with suppliers | 1.9 Plan facility layout for optimal resource flow | 1.10 Define equipment specifications and requirements | 1.11 Assign project team roles and responsibilities | 1.12 Conduct project kickoff meeting | 1.13 Develop communication plan for project updates | 1.14 Schedule initial maintenance setup for key equipment | 1.15 Document all planning procedures and decisions
2.0 Excavation (15 activities)
2.1 Set up and test the Tunnel Boring Machine (TBM) | 2.2 Begin primary excavation work |  | 2.3 Implement safety protocols for excavation | 2.4 Assign labourers and establish excavation schedules | 2.5 Arrange for material deliveries and debris removal logistics |  | 2.6 Perform daily safety briefings for excavation team | 2.7 Monitor material usage and reorder levels for excavation | 2.8 Establish communication channels for excavation progress | 2.9 Coordinate waste removal and recycling during excavation | 2.10 Conduct quality checks on TBM performance | 2.11 Perform weekly equipment maintenance and repairs | 2.12 Document excavation progress and update project timeline | 2.13 Coordinate transportation for debris disposal | 2.14 Train workers on emergency evacuation procedures | 2.15 Adjust excavation plan based on ground conditions
3.0 Lining & Sealing (15 activities)
3.1 Begin concrete mixing and tunnel lining installation | 3.2 Monitor inventory levels of concrete and sealing materials |  | 3.3 Assign equipment operators for lining and sealing machinery | 3.4 Establish waterproofing procedures and apply sealants | 3.5 Schedule ventilation and drainage installation activities |  | 3.6 Conduct safety checks for lining and sealing operations | 3.7 Monitor temperature and humidity during concrete setting | 3.8 Perform bi-weekly maintenance on lining equipment | 3.9 Document material usage and monitor stock levels | 3.10 Review and inspect installed lining for quality control | 3.11 Coordinate logistics for sealant material deliveries | 3.12 Update project timeline based on sealing phase progress | 3.13 Inspect and adjust ventilation equipment installation | 3.14 Establish fire safety protocols for sealing materials | 3.15 Conduct training for workers on sealant application
4.0 Quality Assurance (8 activities)
4.1 Conduct structural and safety inspections for completed sections | 4.2 Review quality of materials used in each phase |  | 4.3 Conduct system testing for tunnel safety | 4.4 Perform final adjustments as needed based on inspection results | 4.5 Document results of quality inspections and system tests |  | 4.6 Perform a comprehensive maintenance inspection of all equipment | 4.7 Schedule additional repairs or adjustments as needed | 4.8 Finalise safety protocols for completed tunnel sections
5.0 Maintenance & Control (16 activities)
5.1 Update equipment records and document condition for handover | 5.2 Develop a punch list of items needing adjustment |  | 5.3 Conduct follow-up inspections to ensure all adjustments are complete | 5.4 Coordinate final approval from safety inspectors | 5.5 Perform mock drills for emergency preparedness |  | 5.6 Organise a project review meeting for quality assessment | 5.7 Finalise and distribute quality inspection reports | 5.8 Develop a preventive maintenance schedule for equipment | 5.9 Assign maintenance personnel for routine tasks | 5.10 Perform monthly preventive maintenance checks | 5.11 Conduct quarterly inspections of heavy machinery | 5.12 Review and update equipment maintenance logs | 5.13 Establish spare parts inventory and reorder levels | 5.14 Train maintenance staff on critical equipment handling | 5.15 Conduct final equipment inspections before handover | 5.16 Archive all maintenance and project documentation

## Phase Summary
Phase Summary
WBS ID | Phase | Activity Count | Share of Total
1.0 | Design & Planning | 15 | 21.74%
2.0 | Excavation | 15 | 21.74%
3.0 | Lining & Sealing | 15 | 21.74%
4.0 | Quality Assurance | 8 | 11.59%
5.0 | Maintenance & Control | 16 | 23.19%
| Total | 69 | 100%